## Sheet1
Functionalitate | Prioritate Functionalitate | Task | Estimare Task | Status | Filip Albert | Dobre Cosmin
Search | low | graphic interface for search | 1 h | in progress |  | x
| low | Implement search function | 1 h | in progress |  | x
Sort | low | graphic interface for sort | 50 min | in progress |  | x
| low | Implement sort function | 50 min | in progress |  | x
Register (guest) | high | graphic interface for register | 20 min | in progress |  | x
| high | Implement register function | 20 min | in progress |  | x
Login (customer) | high | graphic interface for login | 25 min | in progress | x
| high | Implement login function | 25 min | in progress | x
Log-out (customer) | low | graphic interface for log-out | 25 min | in progress | x
| low | Implement log-out function | 25 min | in progress | x
Manage account (customer) | medium | graphic interface for manage account | 2 h | in progress |  | x
| medium | Implement manage account function | 2 h | in progress |  | x
Add item to cart (customer) | medium | graphic interface for adding to cart | 30 min | in progress | x
| medium | Implement adding to cart function | 30 min | in progress | x
Remove item from cart (customer) | medium | graphic interface for removing from cart | 30 min | in progress | x
| medium | Implement removing from cart function | 30 min | in progress | x
Add item to favorite (customer) | medium | graphic interface for adding to fav | 30 min | in progress | x
| medium | Implement adding to fav function | 30 min | in progress | x
Remove item from favorite (customer) | medium | graphic interface for removing from fav | 30 min | in progress | x
| medium | Implement removing from fav function | 30 min | in progress | x
Confirm order (customer) | high | graphic interface for confirm order | 30 min | in progress |  | x
| high | Implement confirm order function | 30 min | in progress |  | x
Order details (customer) | high | graphic interface for order details | 30 min | in progress |  | x
| high | Implement order details function | 30 min | in progress |  | x
Delivery details (customer) | high | graphic interface for delivery details | 30 min | in progress |  | x
| high | Implement delivery details function | 30 min | in progress |  | x
Contact us (customer) | medium | graphic interface for contact us | 20 min | in progress | x
| medium | Implement contact us function | 20 min | in progress | x
Login (admin) | high | graphic interface for login | 25 min | in progress |  | x
| high | Implement login function | 25 min | in progress |  | x
Log-out (admin) | low | graphic interface for log-out | 25 min | in progress |  | x
| low | Implement log-out function | 25 min | in progress |  | x
Add product (admin) | medium | graphic interface for add product | 30 min | in progress | x
| medium | Implement add product function | 30 min | in progress | x
Delete product (admin) | medium | graphic interface for delete product | 30 min | in progress | x
| medium | Implement delete product function | 30 min | in progress | x
Update product (admin) | high | graphic interface for update product | 30 min | in progress | x
| high | Implement update product function | 30 min | in progress | x
History Order (admin) | high | graphic interface for history order | 1 h | in progress |  | x
| high | Implement history order function | 1 h | in progress |  | x